Marketing, Launch & Revenue Plan

RoadMate

Go-to-Market Strategy

Companion to the RoadMate PRD v1.0

Version 1.0

Prepared July 2026

# Table of Contents

# 1. Go-to-Market Philosophy

RoadMate's value only exists once there is enough supply density in a small area for search results to feel reliable. The go-to-market plan is therefore supply-first and hyperlocal: win one set of Calicut neighbourhoods completely before expanding, rather than spreading thin across the city on day one.

## 1.1 Launch sequencing principle

Supply (verified shops/mechanics) is recruited and seeded before any consumer-facing marketing spend, so that the first wave of consumer users who try the product get a genuinely useful result rather than a sparse, disappointing directory.

# 2. Pre-Launch (Weeks -6 to 0)

## 2.1 Supply seeding

- Use Google Places data to build an initial long-list of tyre shops, mechanics, battery dealers, and fuel-delivery contacts in the launch neighbourhoods (Section 3.4 of the PRD flags this as needing primary verification, not just scraping).

- Visit or call the highest-density category (tyre/puncture shops) first, since that is the single most common breakdown and the best proof-of-concept category.

- Offer free listing enrichment in exchange for accurate hours, pricing bands, and a photo — this is a manual, high-touch process for the first 100–150 listings, not a self-serve flow yet.

- Target a minimum viable density before any public launch: at least ~15 verified listings per core category within the launch radius (see PRD Section 15.1 success metric).

## 2.2 Landing page & waitlist

- A simple landing page collects waitlist signups and doubles as an early willingness-to-pay signal for the future Premium Membership (Section 4 open research item in the PRD).

- Local SEO groundwork: Google Business Profile presence, city + category landing pages ("tyre puncture shop near Calicut") built for organic search, launched ahead of the product itself.

# 3. Launch Week

## 3.1 Channels

| Channel | Role at launch |
| --- | --- |
| Local WhatsApp & community groups | Highest-trust channel in Kerala for a hyperlocal service; direct outreach in resident and commuter groups covering the launch neighbourhoods |
| Instagram/Facebook local ads | Geo-targeted ads within the launch radius, creative built around the "breakdown at night" and "who do I even call" pain points |
| Shop-partner cross-promotion | Recruited shops display a RoadMate window sticker/QR code, converting their existing walk-in traffic into app awareness |
| Local press / city blogs | A Calicut-focused tech/startup story angle: "Google Maps + Swiggy, for the roadside" |
| College and ride-share/delivery-rider communities | High breakdown frequency, high smartphone fluency, strong word-of-mouth propagation |

## 3.2 Launch-week goals

- Hit the minimum viable listing density in at least 2–3 launch neighbourhoods before any paid promotion begins.

- Track the Section 15.1 PRD metrics from day one: weekly active searchers, search→action rate, review submission rate.

- Run a manual daily check on "open now" accuracy for the first two weeks — this is the single fastest way to lose first-time-user trust (see PRD Risk table, Section 19).

# 4. Post-Launch Growth (Months 1–6)

## 4.1 Neighbourhood-by-neighbourhood expansion

Rather than opening all of Calicut at once, expand ward-by-ward as each new area reaches the minimum listing density, using the same manual-recruitment playbook proven in launch week. This keeps the "is this actually useful near me" experience consistently strong as the footprint grows.

## 4.2 Retention loop

- Push/SMS re-engagement is deliberately deferred until Phase 2 notifications infrastructure exists; in Phase 1, retention is driven by search quality and word-of-mouth alone.

- Shop-side retention: a simple weekly WhatsApp check-in to keep hours/status fresh doubles as a light-touch relationship-management channel until self-serve owner accounts exist.

## 4.3 SEO plan

- Public, indexable shop-detail pages (Section 2.2's Next.js SSR choice supports this) become long-tail SEO assets — "[category] near [neighbourhood], Calicut" pages.

- Structured data (schema.org LocalBusiness) on shop pages to support rich search results.

- Content: a small set of practical, non-salesy guides ("what to do if your bike won't start at night") that naturally link into the search flow.

# 5. Revenue Rollout

Revenue streams and their phase gating are specified in the PRD, Section 4. This section adds the go-to-market sequencing for each.

| Stream | When to switch on | Go-to-market approach |
| --- | --- | --- |
| Commission per job | Once booking (Phase 2) has enough completed-job volume that a small commission doesn't suppress adoption | Introduce at a low introductory rate for early-cohort workers, with a transparent published rate card |
| Featured/Priority listing | After Phase 1 organic listing density is established | Offer only to already-verified shops in high-search categories, framed as "get seen first," not pay-to-be-listed-at-all |
| Premium membership | Phase 4, only if landing-page waitlist and Phase 2/3 repeat-usage data support willingness to pay | Launch to the existing active-user base first via in-app upsell, not cold acquisition |
| Advertising | Phase 3–4, once there is meaningful traffic to justify sponsor interest | Start with category-relevant local sponsors (tyre brands, fuel stations) before opening to generic ad networks |
| Fleet subscription | Phase 4, as a parallel B2B motion | Direct outbound to Calicut-area delivery/logistics businesses, not a self-serve funnel initially |

# 6. Expansion Roadmap

| Stage | Trigger to proceed |
| --- | --- |
| Calicut (launch city) | Baseline — minimum listing density and Phase 1 success metrics achieved (PRD Section 15.1) |
| Kochi | Calicut shows sustained repeat usage and a validated recruitment playbook that a small team can replicate without founder-level hand-holding |
| Trivandrum | Kochi launch replicates Calicut's metrics within a comparable timeframe, confirming the playbook (not just the city) generalizes |
| Kerala-wide | At least 2 successful city launches with consistent unit economics on commission/listing revenue |
| India | Kerala-wide operations are profitable or on a clear path, and the worker-verification and payments infrastructure (Phase 2–3) has proven reliable at multi-city scale |

Each expansion stage reuses the same phased product roadmap (PRD Section 7) rather than requiring a new build — the product's phase gates are about capability maturity, not city count, so a new city launch is a go-to-market exercise, not a re-engineering one.